## Pre Go Live
Task | Assigned to | Date/s of testing | Pass / Fail | Notes | ACTION REQ'D
Add a journal article to each collection | Sharon
Add a conference paper to each collection | Sharon
Add a book chapter to each collection | Helen
Add a report to each collection | Helen
Add a book to each collection | Helen
Add a Phd Thesis to each collection | Clare G |  | Fail | 1. Its annoying that all the school collections are not listed together, ie SATM Masters, followed by SATM PhD etc - there are other collections in between - which means a lot of scrolling to find the one you want. 2. I cannot seem to find out how to search by supervisor name, to check the format, to maintain consistency of name formats. 3. Date of issue - you have to scroll for the month - there is no drop down menu to choose - too many clicks. 4. Drag and drop file worked. 5. If a compulsory item is missed, although the form will not submit - it does not highlight what is missing, to aid completion. 6. Bellome 2022 uploaded SATM PhD. 7. After uploading it then spools, tried to restart with circle arrow, but continues to spool - showing loading .........., does not go back to start screen, looks like I will have to close the tab completely and open a new one to start an new item. On checking on another tab, the , the community titles are hard to read and differentiate in the current list format - also volume of them is prohibitive - would be helpful if the could hide some of the mutliple ones for the same overall communit behind a dropdown menu - item had loaded. 8. If a second tab is open, it will time out, despite being logged in on another tab and working on that one. 9. Pop up list of names, which comes up when entering Author name, could be useful it it brought up duplicate entries, otherwise not useful. 10. SOM PhD form is similar to what we have now in terms of loading theses - Loaded Borg Cardona with a 1 day embargo - which looks like it is active. 11. Not sure how to set the embargo so that the thesis can be found, but only the title and author/supervisor viewed. 12. No review screen to check what you have entered. 13. It would be helpful if you could stay in the same community to enter theses, rather than have to go right back to the beginning to select a community individually - we often work in batches for a specific school. 14. Can't see an undo button. 15 Ajayi - SWEE loaded. | RD to clarify
Add a Masters thesis to each collection | Clare G |  |  | 1. No supervisor category in the loading form. 2. We do not use Acceptance date. 3. Pop up list of names could be useful it it brought up duplicate entries, otherwise not useful. 4. Started to load a thesis earlier today, and then had to abandon it part way through - cannot seem to navigate to an area where partial submissions might be, to continue from where I left off, so am starting again. 5. Opris is the SATM thesis that I have loaded. 6. SOM - no supervisor field. 7. Chen uploaded. 8. SWEE community does not allow for straight Masters theses - only funded. 9. No supervisor field. 10. No review screen to check what you have entered. 11. Adewole, Oluwatosin Olamiposi entered for SWEE. 12. It would be helpful if you could stay in the same community to enter theses, rather than have to go right back to the beginning to select a community individually - we often work in batches for a specific school. 13. Can't see an undo button.
Add a new collection in existing community | Clare G / Helen / Sharon
Add a new community and a new collection within it | Clare / Rachel | 2024-05-28 | Fail | The form to add an item in the Legoland community is missing supervisors names section and will not allow a file to be uploaded. Did allow me to submit without a file attached. | RD to clarify
Add data to each collection using CERES data submission form | Gemma / Greg
CORD customer submission form | Greg / Gemma / Rachel
Add an embargo to an article | Sharon
Change an embargo on an article | Sharon
Enter a thesis with an embargo | Clare G |  |  | I would like the embargoed theses to show their title and author/supervisor, so that the enquirer can see it exists - the current system does this and allows the enquirer to request to see the thesis - the message comes to me and I then work out if it is possible to give them access/visibility. | RD to clarify
Add an embargo to a thesis | Clare G |  |  | I cannot seem to understand how to do this in the new system, to an existing thesis. 2. When you click on an item to edit it to add an embargo it takes you to a page with 14 pages on it - what are the 14 pages and do we need to amend all 14 pages and all 68 items? 3. Not sure if policy type needs changing. 4. Do we change Withdrawn_read to Read? 5. It is not clear how to reinstate a withdrawn item. 6. Bellome is the thesis that I have restricted until tomorrow, it is showing as restricted, archived and withdrawn! although it is showing withdrawn on CERES, I do no know how to unwithdraw it to see how the restriction works. | RD to clarify
Change an embargo on thesis | Clare G |  |  | See above. | RD to clarify
Add an embargo on a dataset | Gemma / Greg
Change an embargo on a dataset | Gemma / Greg
Add metadata to a published item | Helen
Remove metadata from an item | Helen
Move a record to a different collection | Sharon
Link record to multiple collections (exists in current instance) | Sharon
Deposits from CRIS to CERES including embargo information | Rachel / Clare H
Platform testing of the site: mobile devices, tablets, laptops of different OS and versions and all browsers (Edge 🙁, Chrome, Firefox, Safari, Brave and Android/AppleOS) | Crowd-funded
Accessibility testing
Delete a document | Rachel | 2024-05-28 | Pass | Replaced the CERES Takedown policy with updated version | None
Request a copy of an embargoed article with author's agreement | Rachel | 2024-05-29 |  | Requested a copy of an embargoed item. It sent an email to the author who agreed to share a copy. The item was sent to the requestor successfully. Tested adding additional note to requestor. | None
Search Results | Clare | 2024-05-29 |  | 1. When bringing up theses, it is not clear who the author is, until you click on the individual thesis, as the title has a whole list of names. 2. On Bellome's summary there is what appears a random end of a sentence under the list of names "that leads to feasible transfers." 3. Also need to be able to search by course and/or supervisor. 4. Frustrating that you have to click through to full item page to access file to download thesis. | RD to clarify
Training | Clare | 2024-05-29 |  | 1. I feel I need much more training on how to navigate around this system - its layout and functionality is quite different to the old system, to be able to properly test it as well as use it in the furture. 2. Not sure where I locate items recently added by me. | RD to provide training - I can resolve some of the noted issues.

## After Go Live
Task | Assigned to | Date/s of testing | Notes | ACTION
UI testing with customers | TBC speak to Lauren
AERADE pulling data through OAI to its dspace collections | TBC
CERES submission confirmation email - check URL | Helen / Sharon
IRUS contact / check stats reports working | Shannon / Rachel
Check catalogue metadata upload is working | Shannon
Contact CORE, update / check it is working | Shannon / Rachel
DOI testing | Shannon
reCAPTCHA set up with Google | Shannon